## Task List
Task | Assigned to | Progress…… | Comments /mails..
Add file sizes that needs to be transferred to performance spreadsheet | Pradeep | Done
Support for multiple input files? | Pradeep | Progress.. | Need to check how hadoop handles multiple files.
Performance evaluation of Python MR, C++ MR, Hadoop MR | Pradeep | Progress.. | Need to repeat some of the tests.. Some of the tests for C++ & Python completed but need to be repeated again.
Design MR for BFast: - how can bfast parameters be integrated into API for map tasks | Shantenu/ Sharat/ Kim | Not done
Design match/alignment scenario that utilizes MapReduce | Pradeep | Not done
Different input data sizes: 1, 2, 4, 8, 16 ... 1024 GB (e.g. using the freebase data dumps: http://www.freebase.com/) | Pradeep | Not done
Different number of map/reduce tasks: 1-512 | Pradeep | Not done
Different file systems: Local (/tmp), Lustre (/work), NFS (/home) | Pradeep | Not done
Distribute data among workers .. Making sure that all the workers are engaged at every instance.. | Pradeep | Not done
Get formula to decide the number of reduces… Check hadoop definitive guide | Pradeep | Not done
Add one more use case for performance evaluation- which is varying number of reduces….keeping other parameters same. | Pradeep | Not done
Repeat the degree of freedom tests with Python MapReduce on futuregrid cloud virtual machines.. | Pradeep | Not done
Distributive tests with Python MapReduce on futuregrid cloud virtual machines.. | Pradeep | Not done
Low Priority But should be implemented
Implement Local Python MapReduce without bigjob | Pradeep | Not done
Logical chunking |  | Not implementing. | Whats the performance gain /loss implementing that in python MR..

## Documentation
Task | Assigned to
Documentation involves | Pradeep
1. What is MapReduce? | Done
2. Why MapReduce? | Done
3. How SAGA C++ MapReduce implemented?
4. Why do we need new SAGA Python based MapReduce? | Done
5. What are the design differences between SAGA C++ MapReduce, SAGA Bigjob based python mapreduce.
* what is the performance impact of these differences?
6. Whats the performance of SAGA python mapreduce without bigjob tool?
7. What advantages / performance improvement did SAGA BigJob based python mapreduce provide.
8. What disadvantages did SAGA BigJob based python mapreduce provide? Any ideas how to improve them?
9. How logical chunking affects the performance of SAGA Python Mapreduce?
10. Performance comparision between Hadoop/SAGA C++/ SAGA Python Mapreuduces.
11. What formats does python mapreduce support?
12. What are the different level of mapreduces SAGA Python Mapreduce can exhibit
13. why bfast requires mapreduce.
14. Whats the mapfunction provided by bfast.
15. What is the fileformat bfast uses.
* what is the performance impact of these differences?